## Cover
Appendix 2 TAL STRATEGIC PLAN LOGICAL FRAMEWORK 2006

## Goal
Terai Arc Landscape (TAL) Strategic Plan -Monitoring Plan
Narrative Summary | Indicators (what you will measure?) | Means of Verification (how you will measure this indicator?) | Assumptions related to indicator | Frequency (when you will measure this indicator?) | Responsibility (who will measure this indicator?) | Baseline data (does it exist?) | If no baseline data, who, when and how will it be collected? | Estimated cost to monitor this indicator/collect baseline | Relevant Donor (Activity Level) | Alignment with WWF Nepal Strategic Plan | Alignment with HMG Priorities | Alignment with Eco-regional Targets/ Milestones | Alignment with PPA Objectives
Programme Goal:
By 2014, to conserve the biodiversity, forests, soils and watersheds of the Terai and Churia Hills in order to ensure the ecological, economic and sociological integrity of the region. | G1 By 2014, restoration and effective management of 450,000 hectare of forest areas in TAL (including 300,000 ha of protected areas). | GIS vegetation mapping, field survey in forested areas, key informant interviews |  | every 5 - 10 years durations | External Consultant
| G2. By 2014 well-being ranking of local people enhanced without increasing pressure on TAL forests | sample hh survey, focus group discussions, field observations |  | every 5 - 10 years durations | External Consultant
| G3. By 2010, increase in habitat of tiger, rhinoceros and elephant from 2000 baseline | field records, interaction with park staff |  | every 5 - 10 years durations | External Consultant | Field records
| G4 By 2010, viable populations of tiger, rhinoceros, and elephant re-established and maintained | Habitat managed records, field observations, park and project records |  | every 5 - 10 years durations | External Consultant | Field records
| G5. By 2010 forest cover in Churia region increase compared to 2000 baseline as a result of sustainable management of Churia Hills. | GIS mapping, field observations, key informant surveys, project documents |  | every 5 - 10 years durations | External Consultant | Field records

## Purpose 1
Narrative Summary | Indicators (what you will measure?) | Means of Verification/Source of Data (how you will measure this indicator?) | Assumptions related to indicator | Frequency/Time Period (when you will measure this indicator?) | Responsibility/Who will be collecting the information? (who will measure this indicator?) | Location (where are you going to do the measurement?) | Baseline data (does it exist?) | If no baseline data, who, when and how will it be collected? | Estimated cost to monitor this indicator/collect baseline | Relevant Donor (Activity Level) | Alignment with WWF Nepal Strategic Plan | Alignment with overall TAL Strategic Plan | Alignment with Eco-regional Targets/ Milestones | Alignment with PPA Objectives |  | Link of Logframe activity (LFA) with the Financial model activities (FMA)
PURPOSE
[15 empty] | LFA | FMA
P1. Governance: By 2014, Good governance is established and institutionalized at all levels through support to policy and advocacy, institutional capacity enhancement and improved coordination among TAL implementing partners. | P1.1 Good governance system – appropriate policy and capacity enhancement reported in place in government, non government, community and private sectors organizations | Policy pronouncements by MFSC and DoF TAL progress report key stakeholders meetings |  | Once in 5 years duration Mid-term evaluation | External consultant | Kathmandu and TAL field areas | [8 empty] | LFA | FMA
| P1.2 Inter-sectoral issues are reported to be addressed through policy harmonization between Forest and Self Governance Act and coordination mechanism at national, regional, district and community level | Coordination meeting minutes |  | Mid term evaluation | External consultant | Kathmandu | [9 empty] | 1. GOVERNANCE
| P1.3 DFCCs, BZMC, CFCCs and other coordinating bodies are institutionalized and functional | Minutes of policy making task force, key stakeholders interview |  | Mid term evaluation | External consultant | All CARP sites | [9 empty] | 1.1 Support Policy revision, formulation and advocacy
| P1.4 By 2014, 19650 housesholds awareness and capacity enhanced through skill development trainings | Project record/register, key informant survey, documents and policies |  | Mid term evaluation | External consultant | Kathmandu and All CARP sites | [8 empty] | A1.1.1 | 1.1.1 New formulation
OUTPUTS | [14 empty] | A1.1.1 | Forestry related policies
O1.1 By 2014, enhanced engagement of TAL implementing partners in policy formulation, revision and advocacy at the regional, national, district and local level | O1.1.1 By 2014, 10 different new policies in Forest, PA management, Soil Conservation and other relavanet sector willl eb formulated. | Number of new policy documents | [12 empty] | A1.1.1 | PA/Species related policies
| O 1.1.2 By 2014 13 different policy in Forest, PA management , Soil Conservation and other relavant sector will be reviewed and made up tod ate | Number of revised policy documents, workshop proceedings | [12 empty] | A1.1.1 | Soil Conservation and Churia W/S related policies
| O1.1.3 Increased number of working partnerships established among relevant interest groups on policy matters affecting livelihoods and biodiversity conservation in TAL | MOU, External Relations Analysis |  | once in 2 years duration starting from 2005 | TAL team | Kathmandu/All CARP sites | [8 empty] | A1.1.1 | Other policies
| O1.1.4 policy recommendations adopted by MFSC to help ensure equitable livelihood benefits to TAL communities from Terai Forests | External Relations Analysis |  | once in 3 years duration starting from 2005 | TAL team | Kathmandu | [9 empty] | 1.1.2 Revision of existing policies
| O 1.1.5 Number of meetings/workshops to strengthen program implementation | Consultation minute records, policy analysis reports |  | once in 3 years duration starting from 2005 | TAL team | TAL areas and Kathmandu | [8 empty] | A1.1.2 | Forestry related policies
O1.2 By 2014, enhanced institutional capacity of community-based organisations, NGOs, and governments at the regional, national and district level. | O1.2.1 Improved planning, monitoring and reporting of supported government and local institutions in TAL | CBO operational Plans Periodic reporting Audit report, key informant interviews |  | once in 3 years duration starting from 2005 | TAL team | TAL field areas | [8 empty] | A1.1.2 | PA/Species related policies
| O1.2.2 By 2006, TAL Strategic Plan implementation mechanism developed and endorsed by TAL partners | TAL SP Implementation Plan, key stakeholders meeting |  | once in 3 years duration starting from 2005 | TAL team | Kathmandu | [8 empty] | A1.1.2 | Soil Conservation and Churia W/S related policies
| O.1.2.3 At least 25 % of community based organisation and NGOs implement equitable decision makings, where decision are make fairly addressing the issue of disparity on the basis of class, caste, ethnicity and gender | Focal group discussions, MOU signed with partners or small grant agreements |  | once in 3 years duration starting from 2005 | TAL team | Kathmandu | [8 empty] | A1.1.2 | Other policies
| O 1.2.4 Government institutions practice good governance and provide diversified types of technical and institutional support to at least 4474 user groups | Stakeholders meeting |  | once in 3 years duration starting from 2005 | TAL team | All CARP sites | [9 empty] | 1.1.3 Policy Advocacy
O1.3 By 2014, partnership and coordination among TAL implementing partners established and enhanced | O 1.3.1 By 2007 Existence of MOU between Nepal and India on transboundary co-operation in TAL | Meeting minutes MOU document |  | yearly meeting review ongoing | TAL team | Kathmandu/India | [8 empty] | A.1.1.3 | Seminars and workshops
| O 1.3.2. Number of transboundary meetings and events at field, district and national levels in TAL | Meeting minutes and reports, key informant surveys |  | yearly meeting review ongoing | TAL team | kathamdu/India | [8 empty] | A.1.1.3 | Training and exposure visits (National)
| O 1.3.3 Establishment of coordination forum as part of TAL SP implementation mechanism to share partners progresses, experiences and ensure alignment of activities to TAL Strategic Plan | MOU, External Relations Analysis |  | once in 3 years duration starting from 2005 | TAL team | Kathmandu | [8 empty] | A.1.1.3 | Training and exposure visits (International)
ACTIVITIES | [15 empty] | 1.2 Strengthen institutional capacity
A1.1.1 Formulation of policies related to forestry, protected areas, species, soil conservation, watershed management and others | [14 empty] | A.1.2.1 | Government agencies at national/Regional level
A1.1.2 Revision of policies related to forestry, protected areas, species, soil conservation, watershed management and others | [14 empty] | A.1.2.1 | Government agencies at district level
A1.1.3 Support capacity for policy and advocacy at the local, national and international level (seminars, workshops, training, exposure tours) | [14 empty] | A.1.2.1 | Non-Government organizations
A1.2.1 Strengthen institutional capacity of community-based organisations, NGOs, DFCC, and governments at the regional, national and district level. | [14 empty] | A.1.2.1 | Community based organizations and their networks (Formation and institutionalization)
A1.3.1 Coordination strengthened among and government agencies and between implementing partners at the national, district and local level | [15 empty] | 1.3 Building coordination among implementing agencies and partners
A1.3.2 Coordination strengthened among government agencies and between implementing partners at the transboundary level | [14 empty] | A.1.3.1 | Coordination among government agencies
[15 empty] | A.1.3.1 | Coordination with different agencies in adjoining hill districts
[15 empty] | A.1.3.1 | Coordination among working partners
[15 empty] | A.1.3.1 | Coordination at Transborder level (national level)
[15 empty] | A.1.3.2 | Coordination at Transborder level (Field level)
1.4 Support DFCC
[15 empty] | A.1.2.1 & A2.6.1 | Establish DFCC
[15 empty] | A.1.2.1 & A2.6.1 | Strengthen DFCC
[15 empty] | A.1.2.1 | Monitoring
[15 empty] | A.1.2.1 | Implement financial decentralization mechanism (eg. trust funds, revenue channeling)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on B19: Dependent on the second country

## Purpose 2
Narrative Summary | Indicators (what you will measure?) | Means of Verification (how you will measure this indicator?) | Assumptions related to indicator | Frequency (when you will measure this indicator?) | Responsibility (who will measure this indicator?) | Location/Where? | Baseline data (does it exist?) | If no baseline data, when & by whom will it be collected? | Estimated cost to monitor this indicator/collect baseline | Relevant Donor (Activity Level) | Alignment with WWF Nepal Strategic Plan | Alignment with HMG Priorities | Alignment with Eco-regional Targets/ Milestones | Alignment with PPA Objectives | }+
PURPOSE | [14 empty] | }
P2. Sustainable Forest Management. By 2014, restoration and effective management of 764,000 ha of TAL forest | P2.1 BY 2014 268,000 ha of degraded forests of TAL area has better regeneration, growing stock, species and age diversity compared to baseline of 2003 | GIS updates, forest inventory |  | Once in 5-10 years duration | External consultant | TAL sites
| P2.2 By 2014, 426,000 ha area of forest in TAL managed under collaborative, community, leasehold forest management modes according to operational plan, user objectives and methodologies, procedures and tools developed by projects and the governemnt | CFUG interviews, field observation, operational plans |  | regular in 5 years duration | external consultant | TAL sites
| P2.3 By 2009 presence of focal plant and wildlife species in TAL forests recorded compare to baseline of 2003 | Research study |  | 5-10 years interval study | Researcher | TAL sites
| 2.4 By 2014 more than 2,450 community forest user groups with 400, 000 households benefited from the management of community forests through equitable distribution of forest products. | key informant interview, focus group discussion, sample hh survey |  | regular in 5 years duration | external consultant | TAL sites
| 2.6 By 2010 More than 15, 500 ha of encroached forest area in different districts subjected to rehabilitation. | Policy documents, GIS updates |  | 5-10 years interval study | external consultant | TAL sites
OUTPUTS
O3.1 By 2009, reduction in grazing pressure in nearby government-managed forest | O3.1.1 Number and diversity of seedlings and saplings per unit area in government-managed forests compared to baseline data (natural regeneration) |  | Regeneration survey/Plot sampling (method used by Yonzon 2003) | April/May (annual for the first 3 years?) | TAL field staff/TAL Coordinator/DRM | Sample plots in 4 sites (Khata, Basanta, Lamahi & Laljhadi | Yonzon (2003), no baseline for Laljhadi | March/April 2006 | ? |  |  |  | 4.3
O3.2 By 2009, 38,000 tonnes of fuelwood saved annually as the result of alternate and efficient energy use and private forestry | O3.2.1 By 2009, 3000 Number of biogas plants and 7000 improved cooking stoves installed and utilized (proxy - number of tonnes of fuelwood saved by one unit of biogas and improved cooking stove, reported collection of fuelwood) -10000 households benefit from alternate energy (Check on the implication) |  | BSP records and household survey sample of use (structured questionnaire) | April/May (every three years after baseline is collected) | TAL field staff/TAL Coordinator/DRM | 6 CARP sites (including RBNP and RSWR BZ) | Bhatta 2004 |  | ? |  |  |  | 4.3
| O3.2.2 By 2009, increased in areas of Private forests compared to baseline survey |  | Household survey sample (structured questionnaire), DFO records, geo referencing GIS | April/May (every three years after baseline is collected) | TAL field staff/TAL Coordinator/DRM | 4 CARP sites | Tiwari 2004 | No baseline in house but with DFO | 2000 |  |  |  | 4.3
O3.3 By 2009, reduction in illegal activites in critical areas (e.g. felling trees, illegal selling, encroachment, forest fire, poaching, extraction of NTFPs, overgrazing) | O3.3.1 By 2009, changed in trend in number of recorded incidents of illegal activities |  | CBAPO records, DFO records, focus group discussions, PRA | Annually after 2005 baseline is established (based on previous data) perception based, site wise | TAL field staff/TAL Coordinator/DRM | Basanta, Khata, Mahadevpuri, Laljhadi, Nawalparasi (RCNP BZ) | Data exists but not collated | 2005 | 3000 |  |  |  | 4.5
O3.4 By 2009, 25,000 ha of degraded (as classified 2001 Land SAT TM) TAL forest under restoration SEPARATE RESTORE, MANAGE AND PROTECT TARGETS | O3.4.1 Age class structure, number and diversity of trees, seedlings and saplings per unit area in forests under restoration compared to baseline data (natural regeneration and plantation) |  | Plot sampling (methods used by Yonzon 2003 & DFRS), Survival survey | April/May (every three years after baseline is collected) | TAL field staff/TAL Coordinator/DRM | 6 CARP sites | Yonzon (2003), DFRS | NA | 10000 |  |  |  | 1.3
|  |  | GIS map, ground verification survey | GIS map updated every three years (June) | TAL field staff/TAL Coordinator/DRM (GIS unit) | 6 CARP sites | Forest classification data 2003 |  | ? |  |  |  | 1.3
O3.5 By 2007, formation and establishment of 75 community forest user groups (CFUGs) in TAL for effective community management | O3.5.1 By 2007, 75 Number of CFUGs formed and legalized |  | CF operational plans | Annually after 2001 (based on previous data) | TAL team | 6 CARP sites | 2002 Dr. Kandels report | [5 empty] | 4.6
| O3.5.2 By 2007, 100% of yearly targets delivered by CFUGs |  | CFCC evaluation of CFUGs against operational plans |  | CFCC | 6 CARP sites | DFO report 2004
O3.6 By 2007, effective management of 70,000 ha of TAL forest under various decentralised forest management schemes INDICATORS??? | O3.6.1 By 2007, 5000 ha Area of forest managed under collaborative forest management mode |  | District Forest Management Plan PA/DFO reports (includes outside protected areas figures only) | Annual (based on previous data) | TAL team | 4 CARP sites | DFO report 2004 | [5 empty] | 1.2
| O3.6.2 By 2007, 100% of yearly targets delivered by CFM groups |  | CFM group reports | Annual (based on previous data) | TAL team
O3.7 By 2009, 200 hectares of forest leased to and benefits poor and marginalized households | O3.7.1 By 2009, 200 ha Area of forest leased to poor and marginalized households |  | Leasehold forest operational plans | Annually started from 2004 | TAL team | 4 CARP sites | DFO report 2004 | [5 empty] | 1.2, 4.6
| O3.7.2 By 2009, 500 no of Household income earned from utlilization of leasehold forest |  | DFO reports Leasehold forestry groups records | 2005 onwards | TAL team | 4 CARP sites | DFO report 2004
O2.1 By 2014 268, 000 hectares of degraded forest in TAL subject to restoration through plantation, natural regeneration and reclamation of the encroached areas. | O2.1.1 Age class structure, number and diversity of trees, seedlings and saplings per unit area in TAL forests under restoration increased compared to baseline data (natural regeneration and plantation) | Forest inventory, GIS verification |  | once in 5 years duration starting from 2005 | TAL team and Field staff | All CARP sites
O2.2 By 2014, 90,000 Tonnes of fuelwood saved annually as the result of alternate and efficient energy use (Biogas and Improved cooking stoves) | O.2.1.2 By 2009, 12,000 biogas plants and 35,000 improved cooking stoves installed and utilized in TAL (proxy - number of tonnes of fuelwood saved by one unit of biogas 4.5 Tonne and improved cooking stove 1 Tonne) | hh survey, field observation, field reports |  | once in 3 years duration starting from 2005 | TAL team and Field staff | All CARP sites
O2.3 By 2014, effective management of 426,000 ha of TAL forest under various decentralised forest management modes | O 2.3.1 By 2014 New Operational Plans for 245,000 ha of TAL forest is prepared, approved and put for implementation | management plans, key stakeholders interview |  | once in 3 years duration starting from 2005 | TAL team | All CARP sites
| O2.3.2 By 2009, reduction in grazing pressure in nearby government-managed forest in TAL | Field observation, key informant interview, livestock survey report |  | once in 3 years duration starting from 2005 | TAL team and Field staff | All CARP sites
O2.4 By 2014, sustainable management of TAL forest products and services enhanced | O 2.4.1 Supply of forest products obtained from the sustainable managed forest increased compared to base year in 14 districts in TAL | field observation, key informant interview, CFUG interviews |  | once in 3 years duration starting from 2005 | TAL team and Field staff | All CARP sites
O2.5 By 2014, reclaimation of encroached forest area from TAL districts | O 2.5.1 More then 15, 000ha of the encroached forests in TAL reclaimed. | GIS data base on reclaimed lands, field observation, key informant interviews |  | once in 3 years duration starting from 2005 | TAL team and Field staff | All CARP sites
O2.6 Implementation of sustainable forest management mechanisms strengthened | O2.6.1 District forest sector Plan prepared for 14 districts to initiate effective management in more than 649, 000 ha of forests | CFUG interviews, field observation |  | once in 3 years duration starting from 2005 | TAL team and Field staff | All CARP sites
| O2.6.2 Infrastructure and logistic support for SFM increased | CFUG interviews, field observation |  | once in 5 years duration starting from 2005 | TAL team | All CARP sites
| O2.6.3 Forest policies reviewed and researches conducted in different areas to strenghten SFM | Policy documents, key stakeholder interviews |  | once in 5 years duration starting from 2005 | TAL team | Kathmandu
| O.2.6.4 Community based forest protection system strengthened and enhanced across the TAL forest area | CFCC interviews, field observation, CFUG documents or operational plans |  | once in 5 years duration starting from 2005 | TAL team | All CARP sites
| O 2.6.5 DFCC fully functional and effective across the 14 TAL districts | field observation, key informant interviews, DFCC operational modality document |  | once in 5 years duration starting from 2005 | TAL team | All CARP sites
ACTIVITIES
A3.1.1 Technical support to CFUGs in the incorporation of sustainable grazing management practices into CFUG operational plans and support implementaton (rotational grazing, grass cutting, demarcation of blocks, plantation, fodder production, forage production)
A3.2.1 Promotion of private forestry in CARP sites (through the creation and legalisation of Private Forest Owners Network, expansion of private forest for multi-purpose use)
A3.2.2 Promotion and provision of alternate energy technologies (installation, capacity building, extension services for biogas, improved cooking stoves, microhydro, etc) to targeted households and institutions
A2.1.1 Restoration of degraded forests through , natural regeneration and government, community, leasehold and private plantation | [16 empty] | Link of the Financial Plan activity with the logframne activity (LFA)
A2.1.2 Technical and financial support to CFUGs, CFMGs, district forest office and community-based anti-poaching operations (CBAPO) to reduce forest degradation
A2.2.1 Promotion of alternate energy sources (eg. biogas and ICS) | [15 empty] | LFA | Finnacial Model
A2.3.1 Development and implementation of district and community-based sustainable forest management plans | [16 empty] | 2. SUSTAINABLE FOREST MANAGEMENT
A2.4.1 Enhanced capacity of key service providers and other agencies including CFUGs working in TAL areas to maximise the biodiversity benefits to the lcaal communities | [16 empty] | 2.1 Restore Degraded Forest
A2.5.1 Support DOFs and CFCCs in preventing encroachment and reclaim lands | [15 empty] | A2.1.1 | Plantation by government agencies
A2.6.1 Supporting activities for sustainable forest management (institutional infrastructure development, priority research and studies, periodic assessments and logistical support for field staff) | [15 empty] | A2.1.1 | Plantation by Communities
[16 empty] | A2.1.1 | Natural Regeneration
[16 empty] | A2.1.1 | Private Plantation
[16 empty] | A2.1.1 | Restoration at Leasehold forest land
2.2 Reduce forest degradation through better protection
[16 empty] | A2.1.2 | Support CFUG to Reduce Forest Degradation
[16 empty] | A2.1.2 | Support CFMG to Reduce Forest Degradation
[16 empty] | A2.1.2 | Support Government District Forest Office to Reduce Forest Degradation
[16 empty] | A2.1.2 | Support CBAPO
2.3 Sustainable management of the TAL Forest
[16 empty] | A2.3.1 | Develop Community Forest Operational Plans
[16 empty] | A2.3.1 | Develop Collaborative Forest Management Plans
[16 empty] | A2.3.1 | Develop District Forestry Sector Plan
[16 empty] | A2.3.1 | Implement Community Forest Operational Plans
[16 empty] | A2.3.1 | Implement Collaborative Forest Management Plans
[16 empty] | A2.3.1 | Implement District Forestry Sector Plan
[16 empty] | A2.3.1 | Revolving fund for forest harvest
[16 empty] | A2.3.1 | Develop Leasehold Forestry Plan
[16 empty] | A2.3.1 | Implement Leasehold Forestry Plan
2.5 Sustainably harvest NTFP
[16 empty] | A2.3.4.1 | Provide Seed Capital
[16 empty] | A2.3.4.1 | Training
2.6 Reclaim Encroached Forest Land
[16 empty] | A2.6.1 | Database Creation
[16 empty] | A2.6.1 | Maintain Database
[16 empty] | A2.5.1 | Evacuation of Encroachment
[16 empty] | A2.5.1 | Restore Encroahed Forest
0
Note on B12: Qualitative information due to unclear baseline, perception, case studies
Note on A15: Degraded forest management
Note on B23: santosh.nepal: Managed area under CF & CFM = 426,000 Already CF = 181,000, NO CFM Plans New plans need to prepared= (426,000- 181,000)= 245,000 ha
Note on B3: santosh.nepal: Plantation by governemnt: 31, 548 ha Plantation by community: 37,869 ha Natural regeneration : 176, 722 ha Leasehold forestry (poor): 5,049 ha Rehabilitation (encroached land): 15,515 ha Total: 267,975ha
Note on B4: santosh.nepal: CF area: 258,609 ha CFM arae: 162,325 ha LF area: 5,049 ha Total : 425,983 ha
Note on A42: santosh.nepal: The budgeted activities is in governence for DFCC
Note on A38: santosh.nepal: The budgeted activity is in 5.5 (sustainable livelihoods)

## Purpose 3
Narrative Summary | Indicators (what you will measure?) | Means of Verification (how you will measure this indicator?) | Frequency (when you will measure this indicator?) | Responsibility (who will measure this indicator?) | Location | Baseline data (does it exist?) | If no baseline data, who, when and how will it be collected? | Estimated cost to monitor this indicator/collect baseline | Assumptions related to indicator | Relevant Donor (Activity Level) | Alignment with WWF Nepal Strategic Plan | Alignment with Overall TAL Strategic Plan | Alignment with Eco-regional Targets/ Milestones | Alignment with PPA Objectives
PURPOSE
P3.Species & Ecosystem Conservation. By 2014, viable populations of tiger, elephant, rhino and other species of special concern and their habitats are re-established and maintained in TAL. | P3.1 Populations of tiger, rhinoceros, and elephant stabilised by 2006, and increased by 2010, compared to 2000 baseline | Census report, regular patrolling records | conduct census in 3- 5 years interval as per the species | WWF Nepal/ TAL team/ external experts | 4 TAL Protected Areas | DNPWC records
| P3.2 free movement of wild animals increased compared to baseline 2005 through the management of linkages and corridors from one protected area to another | field monitoring reports, groups meetings, PRA mapping | regular survey to be conducted in 5 years duration | WWF Nepal/ TAL team/ external experts | All CARP sites | Field reports
| P 3.3 N no of identified representative forest ecosystems reported to show intactness of Y no of indicator plants and animals species | Forest inventory, research reports | update reports in 10 years interval | Researcher/Consultants | All CARP sites
| P 3.4 3 degraded wetland ecosystems regained its original condition compared to year 2005 | Research reports, monitoring reports | update reports in 10 years interval | Researcher/Consultants | All CARP sites
| P3.5 N no of vulnerable naturally occurring species in agro-biodiversity are regained in its original condition by the year Y | Research reports, monitoring reports | update reports in 10 years interval | Researcher/Consultants | All CARP sites
OUTPUTS
O5.1. By 2006, to maintain and improve existing habitat within protected areas in TAL | O5.1.1 By 2006, habitat area (within protected areas) at least equal to 2003 measured by habitat use of flagship species and evidence of expanding distribution of wildlife. | Park records, research reports, annual report | 2001 onwards annually | Field staff/DRM | Within 4 Pas | Park Management Plan, Vegetation monitoring report, GIS analysis grassland workshop report | [6 empty] | 1.4
O5.2 By 2006, to safeguard the viability of rhino and tiger populations in TAL through active biological management | O5.2.1 Second viable population of rhino (>100) established at RBNP and third population of rhino established (20) in RSWR while maintaining the source population of rhinos at RCNP (Assumption) | Rhino translocation report, Park Records, Monitoring reports | 2002 onwards annually | TAL Kathmandu/PA & BZ program/DRM | RSWR, RCNP and RBNP | Rhino count report | NA | [5 empty] | 2.2, 2.3, 2.7
| O5.2.2 Tiger (123 breeding) shown to stabilised and maintained or increased from 2000 (DNPWC) baseline | Park records, research reports, annual report
O5.3 By 2006, to, reduce illegal killing of rhinos, tigers and other important wildlife in TAL to levels where they no longer threaten their viability | O5.3. 1 Tiger (123 breeding) shown not to decrease from 2000 (DNPWC) baseline | Park records, research reports, annual report | 2002 onwards annually | TAL Kathmandu/PA & BZ program/DRM | RSWR, RCNP and RBNP | Tiger Action Plan | [6 empty] | 2.1, 2.2, 2.3, 2.7
| O5.3.2. Reduction in the reports of poaching incidents of rhino from the 2003 baseline as measured against effort | Park records, research reports, annual report | 2002 onwards annually | TAL Kathmandu/PA & BZ program/DRM | RSWR, RCNP and RBNP | Rhino action Plan | [6 empty] | 2.5
| O5.3.3. Comparison of rhino population with 2003 baseline | Rhino count report, monitoring report | 2002 onwards annually | TAL Kathmandu/PA & BZ program/DRM | RSWR, RCNP and RBNP | Rhino action Plan | [6 empty] | 4.2
5.4. By 2005, to develop and put in place an effective plan to address emerging human wildlife conflict issues | O.5.4.1 Development and implementation of a human wildlife conflict mitigation strategy in consultation with stakeholders and especially the local communities by 2005 | Mitigation strategy document | 2005 onwards annually | TAL Kathmandu and WTLBP | CARP sites | Livestock and depradation reports | [6 empty] | 4.2
| O5.4.2 Perception/attitude of people of pilot sites on the effects of mitigation measures | Case studies, BZ/CFCC records, parks records (complaints reported) | continued annually | Field staff/DRM | CARP sites | various study reports | [6 empty] | 4.2
5.5. By 2007, status surveys of dolphin populations asssesed in rivers in TAL | O5.5.1 By 2007, Dolphin population survey published as baseline information | Census report | 2007 once and follow up as per the monitoring recommendation | Fresh Water Unit | Karnali, Narayani, Mohana | Bhoj Raj Shrestha report, KMTNC report | [6 empty] | 2.7
5.6 By 2009, 1 Ramsar sites under effective management in TAL | O5.6.1 By 2006, management of 1 Ramsar site initiated | Annual Progress Report | 2006 onwards | Fresh Water Unit | Kailali, Ghodaghodi | Management plans prepared by the community
O3.1 By 2014, improved management of protected areas and buffer zones in TAL | O3.1.1 habitat area (within protected areas) in TAL at least equal to 2003 measured by habitat use of flagship species and evidence of expanding distribution of wildlife. | Park records from monitoring, research reports, annual report | once in every 3 years duration starting from 2005 | Researcher/Consultants | TAL 4 Protected Areas
O3.2 By 2014, improved wetland and agro-biodiversity management outside protected areas in TAL | O3.2.1 representative targeted floral and faunal species densities increased in forest, agriculture and wetland ecosystems from the baseline 2005 | Forest inventory, research reports | once in every 5 years duration starting from 2005 | Researcher/Consultants | All CARP sites | [10 empty] | 3. SPECIES AND BIODIVERSITY CONSERVATION
| O3.2.2 Quality of 7 out of 23 no of identified representative forest ecosystems maintained | Forest inventory, research reports | once in every 5 years duration starting from 2005 | Researcher/Consultants | All CARP sites | [10 empty] | 3.1 Enhance Biodiversity Conservation in the Protected Areas
| O3.2.3 3 no of degraded wetland ecosystems regained | Research reports, monitoring reports | once in every 5 years duration starting from 2005 | Researcher/Consultants | All CARP sites | [9 empty] | A 3.1.1. | Create/Revise PA Management Plans
O3.3 By 2014, effective management of key plant and wildlife species in TAL | O3.3.1 Action Plans for key plants and wildlife species developed and implemented | Action plan documents, key interviews | update once in 2 years duration ongoing | Researcher/Consultants | All CARP sites | [9 empty] | A 3.1.1. | Create/Revise BZ Management Plans
| O3.3.2 Endangered species viable population maintained through translocation | field records, database reports | update once in 2 years duration ongoing | TAL team and field Officer | CARP sites (focus more on PA) | [9 empty] | A 3.1.1. | Implement PA Management Plans
| O3.3.3 Wildlife orphanages supported to manage the problem animals | field records and key informant interview | update once in 2 years duration ongoing | TAL team | CARP sites (focus more on PA) | [9 empty] | A 3.1.1. | Implement BZ Management Plans
O3.4 By 2014, reduction in poaching and illegal trade of plant and wildlife species in TAL | O3.4.1 Tiger population (123 breeding) shown not to decrease from 2000 (DNPWC) baseline | camera trapping, field survey, park monitoring records, census reports | update once in 2 years duration ongoing | TAL field Officer | CARP sites (focus more on PA) | [10 empty] | 3.2 Enhance Biodiversity Conservation Outside the Protected Areas
| O3.4.2. Reduction in the reports of poaching incidents of rhino in TAL from the 2003 baseline as measured against effort | houshehold surveys, group discussions, case studies, monitoring reports | once in every 3 years duration ongoing | TAL team | CARP sites | [9 empty] | A 3.2.1. | Create/Revise Agro Biodiversity Plan
| O3.4.3. Comparison of rhino population with 2003 baseline in TAL | Census report, regular patrolling records | update in every 3-5 years interval ongoing | TAL team/external experts | TAL 4 Protected Areas | [9 empty] | A 3.2.1. | Create/Revise Wetland Biodiversity Plan
O3.5 By 2014, impacts on local people from human/wildlife conflict reduced | O.3.5.1 Development and implementation of a TAL human wildlife conflict mitigation strategy in consultation with stakeholders and especially the local communities by 2005 | houshehold surveys, group discussions, case studies, monitoring reports | once in every 3 years duration starting from 2005 | TAL team/Livelihood espcialist | All CARP sites | [9 empty] | A 3.2.1. | Implement Agro Biodiversity Plan
| O3.5.2 Perception/attitude of people at TAL pilot sites on vulnerability and the effects of mitigation measures | Case studies, BZ/CFCC records, parks records (complaints reported) | once in every 3 years duration starting from 2005 | TAL team/Livelihood espcialist | All CARP sites | [9 empty] | A 3.2.1. | Implement Wetland Biodivesity Plan
O3.6 By 2014, database system established for effective wildlife and habitat management | O. 3.6.1 Wildlife and habitat management database managed effectively | [14 empty] | 3.3 Conduct research/studies on landscape level conservation
O3.7 By 2014, local comunities are awere with the conservation imporatnce of the landscape and its biodiversity | O. 3.7.1 School based ecoclubs and their networks increased in all the districts of TAL | [13 empty] | A 3.2.1. | Conduct wetland inventory
| O. 3.7.2 Increased community led eco friendly and wildlife conservation initiatives in the landscape | field records, database reports | once in every 5 years duration starting from 2005 | TAL team/Livelihood espcialist | All CARP sites | [9 empty] | A 3.2.1. | Conduct Agro Biodiversity inventory
ACTIVITIES | [14 empty] | A 3.3.1. | Endangered species study (Action plans)
A3.1.1 Development and implementation of PA and BZ Management Plans | [14 empty] | A 3.6.1. | Wildlife monitoring and database
A3.2.1 Development and implementation of wetland and agro-biodiversity management plans | [14 empty] | A 3.6.1. | Priority research (need and implications including international conventions e.g; WTO, wildlife farming)
A3.3.1 Support development and implementation of endangered species action plans | [14 empty] | A 3.6.1. | Small Grant Research
A3.3.2 Support for translocation of targeted species | [14 empty] | A 3.3.2. | Species management (Translocation of selected species, captive breeding)
A3.3.3 Management of problem animals Identify and control of invasive plant species | [14 empty] | A 3.3.1. | Key Species action plan implementation
A3.4.1 Support for implementation of CITES | [14 empty] | A 3.6.1. | Control of invasive plant species
A3.4.2 Support for community-based anti-poaching operations | [15 empty] | 3.4 Conduct conservation education and awareness
A3.5.1 Development and implementation of human/wildlife conflict mitigation strategies and mechanisms | [14 empty] | A 3.7.1. | Establish and support Eco Clubs and their network
A3.6.1 Support for wildlife monitoring and research | [14 empty] | A 3.7.1. | Establish and support information centers
A3.7.1 Support and strengthen eco-clubs and their networks | [14 empty] | A 3.7.2. | Conduct Awareness Campaigns/events
A3.7.2 Develop and conduct conservation education and comunication campaigns | [14 empty] | A 3.7.2. | Communication (Publications, audio visual means)
[15 empty] | A 3.7.2. | Experience sharing, learning (e.g. PAL Net)
[15 empty] | A 3.7.2. | Conservation education programs (Gothala, agharia, NFE)
3.5 Control wildlife trade
[15 empty] | A 3.4.1 | Implement CITES Requirements (awareness, sensitization etc)
[15 empty] | A 3.4.1 | Strengthening CITES unit
[15 empty] | A 3.4.2 | Support Community Based Anti Poaching Operations (CBAPO)
3.6 Human Wild Life Conflict Mitigation
[15 empty] | A 3.5.1 | Develop HWC mitigation strategy
[15 empty] | A 3.5.1 | Develop mechanism to mitigate HWC (compentiation, insurance etc)
Note on A18: sushila nepali: This is a new addition to reflect the work in the wetlands

## Purpose 4
Narrative Summary | Indicators (what you will measure?) | Means of Verification (how you will measure this indicator?) | Frequency (when you will measure this indicator?) | Responsibility (who will measure this indicator?) | Location | Baseline data (does it exist?) | If no baseline data, who, when and how will it be collected? | Estimated cost to monitor this indicator/collect baseline | Assumptions related to indicator | Relevant Donor (Activity Level) | Alignment with WWF Nepal Strategic Plan | Alignment with HMG Priorities | Alignment with Eco-regional Targets/ Milestones | Alignment with PPA Objectives
PURPOSE
P4. Churia Watershed Conservation. By 2014, integrated watershed conservation and management strengthened to maintain biological corridors and reduce livelihood vulnerability in Churia Hills | P4.1 Key partnerships developed in Churia watershed conservation and management | MOU signed documents, minutes of the meeting
| P4.2 Conducive government policies for Churia watershed management formulated (for example, Churia Hills forest designated as limited use/protection forest) | Policy documents, management plans
OUTPUTS
O6.1 By 2006, development of Churia Strategy (developed by HMG with the support of CARE Nepal, IUCN and WWF Nepal) and initial implementation at pilot sites | O6.1.1 Churia Strategy developed and endrosed by HMG with WWF as key partner | Churia Strategy Document, | 2006 onwards once | TAL Kathmandu | Kathmandu | [7 empty] | 3.2
O6.2 By 2009, increased awareness about the ecological services of Churia among major stakeholders | O6.2.1 By 2009 government declares Churia as protection forest | Gazette notification | 2009 | TAL Kathmandu | Kathmandu | [7 empty] | 3.2
| O6.2.2 By 2009 payment for environmental service initiated at least one site of churia | Policy documents | 2009 onwards | TAL Kathmandu | Kathmandu
O6.3 By 2009, improved co-ordination between partners working in the Churia for implementation of Churia Strategy and integrated watershed management activities | O6.3.1 By 2009 funds leverage increased for integrated watershed management | MOU with partners, Partnership Plan | 2009 onwards | TAL Kathmandu | Kathmandu | [7 empty] | 4.4
O6.4 By 2009, within critical areas in TAL appropriate integrated watershed management activities identified and implemention initiated in partnership with DSCWM | 06.4.1 By 2009 integrated watershed management activities launched | MOU with DSCWM, TAL strategic Plan, Progress report | 2009 onwards | TAL Kathmandu | Kathmandu
O4.1 By 2014, implementation of soil conservation and integrated watershed management plans initiated in TAL | O 4.1.1 165,000ha of critical subwatersheds in 14 TAL districts managed under ISWMP approach.
| O 4.1.2 More than 6,600 ha of critically degraded watreshed area rehabilated through Soil Conservation measures | [14 empty] | 4. SOIL CONSERVATIONAND CHURIA WATERSHED MANAGEMENT
| O 4.1.3 More than 550 Community development groups will be involved in the manageemnt of sub watersheds in 14 TAL districts. | [14 empty] | 4.1 Conduct Land Use Planning
O4.2 By 2014, increased understanding of ecological services, including hydrological functions of Churia Hills | O 4.2.1 Churia region categorized as Special portfolio in the government plans and managed following special land use management | [13 empty] | A4.1.1 | Proritization of sub-watersheds
ACTIVITIES | [14 empty] | A4.1.1 | Develop integrated watershed management plans for priority watersheds
A4.1.1 Develop integrated watershed management plans for priority watersheds | [15 empty] | 4.2 Implementation of SWS plans
A4.1.2 Support for implementation of integrated watershed management plans | [14 empty] | A4.1.2 | Land rehabilitation and Productivity Improvement
A4.1.3 Development and implementation of inter sectoral coordination mechanism in TAL for sustainable watershed management | [14 empty] | A4.1.2 | Micro W/S management
A4.2.1 Conduct research supporting sustainable watershed management in Churia (PES, special port folio to Churia, economic valuation, ground water status survey, extraction study) | [14 empty] | A4.1.2 | Hotspot treatment
[15 empty] | A4.1.2 | Improve community facilities
[15 empty] | A4.1.3 | Community development Group mobilization and empowerment
4.3 Reduce erosion and flood havac with CDG
[15 empty] | A4.1.4 | Study on economic value of Churia
[15 empty] | A4.1.4 | Pilot Payment of environmental services for Churia
[15 empty] | A4.1.4 | Ground water status assessment
[15 empty] | A4.1.4 | Inter sectoral coordination and collaboration mechanism for Sustainable developemnt in watershed perspective
[15 empty] | A4.1.4 | Study on the impact of extraction of quarries and debris from Churia region

## Purpose 5
Narrative Summary | Indicators (what you will measure?) | Means of Verification (how you will measure this indicator?) | Frequency (when you will measure this indicator?) | Location | Responsibility (who will measure this indicator?) | Baseline data (does it exist?) | If no baseline data, who, when and how will it be collected? | Estimated cost to monitor this indicator/collect baseline | Assumptions related to indicator | Relevant Donor (Activity Level) | Alignment with WWF Nepal Strategic Plan | Alignment with HMG Priorities | Alignment with Eco-region Targets
PURPOSE
P5. Sustainable Development. By 2014, improve the livelihoods of 100,000 TAL households in TAL, including poor and marginalized households, without increasing pressure on TAL biodiversity. (add footnote below defining poor and marginalized) | P5.1 At least 10,000 (out of 35,000 TAL households) poor and marginalised households benefiting from sustainable forest, agri-based and off-farm income opportunities | Refer to 3.1.1; temporal comparison of household incomes (sample household survey of intended beneficiary households according to wealth ranking - refer to NLSS 2004) | Once in every 5-10 years interval | all CARP sites | External consultant
| P5.2 increased motivation and participation in conservation activities of local people and institutions in TAL due to perceived benefit from provision of small physical infrastructure and basic services | motivation: focal group discussion with local people and institutions participation: sample community survey - focal group discussions with local people and institutions by external facilitator; household contribution to conservation activities | Once in every 5-10 years interval | All CARP sites | External consultant
| P5.3 35,000 TAL households perceive benefit from provision of community services | sample household survey - focal group discussions with households by external facilitator | Once in every 5-10 years interval | All CARP sites | External consultant | [9 empty] | Link of Logframe activity (LFA) with the Financial model activities (FMA)
OUTPUTS | [13 empty] | LFA | FMA
O4.1 By 2009, 10,000 poor and marginalised households in critical areas in TAL benefit from sustainable forest, agri-based and off-farm livelihood opportunities | O4.1.1 By 2009 increased income levels of 1,000 poor and marginalised households from the baseline status as a result of off farm income generation. | annual report, mid term report, well being ranking report | 2005 onwards annually 2008 mid-term evaluation | All CARP sites | Field staff/DRM/TAL Kathmandu | SAMANATA 1999? Successful communities initiatives 2001 compiled and reviewed 2004 | Well being ranking including baseline survey in all CARP sites needed and will be compiled by field staff by 2005 | 20,000 US |  |  |  |  | 4.1
| O4.1.2 By 2009 increased income level of 3,000 marginalised farmer households from the baseline status as a result of agro-based IGA | annual report, mid term report, well being ranking report | 2005 onwards annually 2008 mid-term evaluation | All CARP sites | Field staff/DRM | SAMANATA 1999? Successful communities initiatives 2001 compiled and reviewed 2004 | [6 empty] | 4.1
| O4.1.3 By 2009 increased income level of 3,300 + 300 (leasehold) marginalised households from the baseline status as a result of forest based IGA. | annual report, mid term report, well being ranking report | 2005 onwards annually 2008 mid-term evaluation | All CARP sites | Field staff/DRM | KK Shrestha 2002 | [6 empty] | 4.1
O4.2 By 2009, 33,000 TAL households have improved access to basic services, particularly poor and marginalized groups | O4.2.1 By 2007 improve access to 30,000 households through community infrastructure | Field observation, annual report, VDC profile | Already happening annually 2008 mid-term evaluation | All CARP sites | Field staff/DRM | BZ management plans Compiled report 2004 Village Profile | [6 empty] | 4.1
O4.1.3 Development & implementation of KCA ecotourism plan
O4.1.4 Increased access of KCA households to basic community support services
| O4.2.1 By 2009 improve health and sanitation of 3,000 marginalised households (drinking water/toilet) | Field observation, annual report, VDC profile | Already happening annually 2008 mid-term evaluation | All CARP sites | Field staff/DRM/TAL Kathmandu | BZ management plans Compiled report 2004 Village Profile | [6 empty] | 4.1
O4.3 By 2009, increase in revenue generation for RSWR and RBNP and households at two pilot sites outside protected areas from ecotourism activities | O4.3.1 By 2009 park revenue increased by 23% in RSWR and RBNP | Park records, annual reports, DNPWC annual report | Continuous annually | All CARP sites | Field staff/DRM/TAL Kathmandu | Park financial reports | [6 empty] | 4.1
| O4.3.2 By 2009, 130 households income increased from eco-tourism outside PA | annual report, case studies | 2008 mid term evaluation | RSWR, RBNP, Khata, Ghodaghodi/Dovan | Field staff/DRM/TAL Kathmandu | Bardia Tourism Plan | Study outside PA to be conducted in 2005 by Kathmandu | [5 empty] | 4.1
O4.4 By 2003, sustainable livelihoods approach framework developed and implemented to identify target groups and design appropriate interventions | O4.4.1 By 2003 guideline developed and implemented/piloted | Sustainable livelihood document, Annual Workplans, Progress Reports | 2005 onwards and monitor annually | All CARP sites | DRM |  | Strategy to be developed by sustainable livelihood officer | [5 empty] | 4.5
O5.1 Increased participation and benefits received by target groups in TAL Programme activities | O5.1.1 25% of the marginalised and poor target groups representated in executive bodies | sample household survey- focoal group discussion | 2005 onwards annually | all CARP sites | TAL team and field staff |  | wealth ranking to be conducted by field staff | 2,000 US | [6 empty] | 5. SUSTAINABLE LIVELIHOODS
O5.2 By 2014, 100,000 households in TAL benefit from sustainable forest, agri-based and off-farm income generating opportunities | O52.1 increased income levels of 1,000 poor and marginalised households in TAL from the baseline status as a result of off farm income generation. | sample household survey - focal group discussions with households by external facilitator | 2005 onwards annually 2008 mid-term evaluation | All CARP sites | TAL team and field staff | [9 empty] | 5.1 Identify and organize target groups
| O5.2.2 increased income level of 5,000 marginalised farmer households in TAL from the baseline status as a result of agro-based IGA | sample household survey among the marginalised groups | 2005 onwards annually 2008 mid-term evaluation | All CARP sites | TAL team and field staff | [8 empty] | A5.1.1 | Conduct well being ranking
| O5.2.3 By 2009 increased income level of 4000 (leasehold) marginalised households in TAL from the baseline status as a result of forest based IGA. | sample household survey among the marginalised groups | 2005 onwards annually 2008 mid-term evaluation | All CARP sites | TAL team and field staff | [9 empty] | Zonation of forest land for IGA activity
O5.3 By 2014, increase in revenue generation for TAL households outside protected areas from ecotourism activities | O5.3.1 By 2009 park revenue increased by 25% in RSWR and RBNP | Park records, annual reports, DNPWC annual report | Continuous annually | RBNP and RSWR | TAL team and field staff | [9 empty] | 5.2 Improve agrobased livelihood
| O5.3.2 By 2009, 150 households income increased from eco-tourism outside PA | focus group discussion and annual reports | 2008 mid term evaluation | RBNP and RSWR | TAL team and field staff | [8 empty] | A5.2.1 | Strengthen agriculture and livestock extension services
O5.4 By 2014, provision and use of small physical infrastructure and basic services to 35,000 TAL households | 5.4.1 50 % of TAL households have access and use the basic services | Field observation, group discussions and annual reports | Already happening annually 2008 mid-term evaluation | All CARP sites | TAL team and field staff | [8 empty] | A5.2.1 | Improve productive infrastructure facilties (e.g. irrigation, crop storage, Wholesale distribution hubs scheme)
ACTIVITIES | [13 empty] | A5.2.1 | Transfer technology to farmers (training, Integrated Pest Management, off season crops, improved seed, inputs, equipments, High value crops etc)
A5.1.1 Conduct well-being ranking to identify target groups | [14 empty] | 5.3 Promote Income Generating Activities (IGA)
A5.2.1 Support for agri-based income generating activities (agriculture and livestock extension services, infrastructure development, technology transfer, capacity building) | [13 empty] | A5.2.1- 3 | IGA Group formation and institutionalization
A5.2.2 Support for off-farm income generating activities | [13 empty] | A5.2.2 | Promote off farm/off forest IGA
A5.2.3 Support for forest-based income generating activities | [13 empty] | A5.2.3 | Promote forest based IGA
A5.3.1 Promote ecotourism in TAL buffer zones and corridors | [13 empty] | A5.2.3 | Promote NTFP based IGA
A5.4.1 Financial and technical support to community services (drinking water schemes, toilets, community irrigation facilities, community service centres, health & sanitation, small infrastructure) | [14 empty] | Skill Development Training
[14 empty] | A5.4.1 | Develop Business Development Information centers
[14 empty] | A5.4.1 | Provide business development services
5.4 Promote ecotourism in Buffer Zone & corridors
[14 empty] | A5.3.1 | Develop Infractstructure (eg. Observation towers, roads bridges, etc)
[14 empty] | A5.3.1 | Training Local People (Guide Training Hospitality Training, Lanuage Training
5.5 Promote alternate energy sources
[14 empty] | A2.2.1 | Biogas plants
[14 empty] | A2.2.1 | Improved Cooking Stoves
5.6 Enhance community services
[14 empty] | A5.4.1 | Small scale community infrastructure
[14 empty] | A5.4.1 | Support for basic services
5.7 Reduce vulnerability
Introduce preventative measures against natural calamities